|  |  |  |  |
| --- | --- | --- | --- |
| **Check** | **To Do** | **Contact** | **Notes** |
| **Deadline: Oct. 1st** | | | |
|  | Proposal presented to the IPRC (If requested) | Penelope | [pjs25@humboldt.edu](mailto:pjs25@humboldt.edu) 3942 |
|  | Additional material requested by the IPRC submitted to CIP (If requested) | Penelope |  |
|  | Part 1 of the Proposal signed by all parties | Penelope |  |
| **Deadline: end of Fall semester** | | | |
|  | Notification of completed routing and approval - program can be actively promoted | Penelope |  |
|  | Contractual Agreements developed and signed | Kim | [Kimberly,Comet@humboldt.edu](mailto:Tawny.Fleming@humboldt.edu) 4273 |
|  | Promotional material for the website sent to CIP | Penelope |  |
|  | Website up to date – students can read about program | Penelope |  |
|  | Post flyers and hold informational meetings | Program Director | Please inform Penelope of info. meeting dates |
|  | Develop final budget\*\* | Carl | Budget template on website [Hansen@humboldt.edu](mailto:Hansen@humboldt.edu) 5877 |
| **Deadline: Spring semester** | | | |
|  | Program can be open for applications once final budget is approved | Penelope |  |
|  | Develop final itinerary and teaching schedule \*\* | Penelope | Template on the website |
|  | Brochures sent to CIP at least two weeks before IEW (held in Feb.)\*\* |  | Template on the website |
|  | Make final decisions on program staffing | Carl |  |
|  | Confirm all dates | Penelope& Carl |  |
|  | Complete Site Assessment documents for programs with internships or Service Learning\*\* | Penelope | Document on the website |
|  | Obtain Certificates of Insurance from transportation providers for any non-public transportation used by the program | Penelope | Must be provided before the start of the program. |
|  | Read Emergency Management Plan – develop procedures – evacuation, phone tree, on-site orientation. CIP will print a copy if you need it. |  | On ‘Faculty’ page [www.humboldt.edu/goabroad](http://www.humboldt.edu/goabroad)  Questions? Ask Penelope 3942 |
|  | Confirm all emergency contact information/SKYPE – Director’s contact numbers, organizations’ numbers, numbers while traveling if different | Penelope& Carl |  |
|  | Work with CEEE to complete Travel Authorizations | Carl |  |
| **Deadline: At least a month before departure** | | | |
|  | Part 2 of the Proposal completed | Penelope | Submit any outstanding documents |
|  | Attend Faculty Workshop in spring semester | Penelope |  |

\*\* Use template/document provided on line at [www.humboldt.edu/goabroad](http://www.humboldt.edu/goabroad) click on the ‘Faculty’ link